## Weekly Tasks
quarter | iteration | week | task_name | owner_email | deadline | category | description
Q2 2026 | 1 | 1 | Analyse Data: MSA + PGs |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 1 | UnSaturated MSAs Transition Plan - Draft |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 1 | CHC Execution Plan - Draft |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 2 | MSAs Transition Plan Final |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 2 | Vision / Strategy Doc Draft |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 2 | CHC Execution Plan Final |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 3 | Vision / Strategy Doc: Final |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 3 | Outreach execution |  |  | Customer Success & PG Acquisition
Q2 2026 | 1 | 1 | MVP Feature Definition Final |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 1 | Orchestrator Workflows (Market + PG + CS) |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 2 | System Architecture |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 2 | DevOps Setup (CI/CD, infra baseline) |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 2 | Dev Team Onboarding + Requirements |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 2 | Orchestrator Workflows - Unit test modules |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 2 | Unit Test: Market Analysis |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 3 | Unit Test: Customer Success |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 3 | Requirements Discussion - Vendors |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 3 | All units built and tested |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 3 | MVP Development Sprint Begins |  |  | Product / Engineering / Workflows
Q2 2026 | 1 | 1 | FTE Engagement |  |  | Cybersecurity
Q2 2026 | 1 | 1 | SOC + HIPAA set up |  |  | Cybersecurity
Q2 2026 | 1 | 2 | GovRamp Plan |  |  | Cybersecurity
Q2 2026 | 1 | 2 | FTE Engagement - Onboarding |  |  | Cybersecurity
Q2 2026 | 1 | 1 | Soul Doc (Culture + Learning): Base Discussions |  |  | Continuous Learning
Q2 2026 | 1 | 2 | Soul Doc (Culture + Learning) |  |  | Continuous Learning
Q2 2026 | 1 | 1 | Engg Vendor Identification |  |  | Talent Acquisition
Q2 2026 | 1 | 1 | Architect Discussion |  |  | Talent Acquisition
Q2 2026 | 1 | 2 | Dev Team Onboarding |  |  | Talent Acquisition
Q2 2026 | 1 | 2 | CyberSec Intern Pipeline + Strategy |  |  | Talent Acquisition
Q2 2026 | 1 | 2 | Engg Onboarding |  |  | Talent Acquisition
Q2 2026 | 1 | 2 | Architect Onboarding |  |  | Talent Acquisition
Q2 2026 | 1 | 3 | CyberSec Interns - Shortlisting |  |  | Talent Acquisition
Q2 2026 | 1 | 1 | Website Draft |  |  | Branding
Q2 2026 | 1 | 1 | Communication Infra Setup |  |  | Branding
Q2 2026 | 1 | 2 | Website Final |  |  | Branding
Q2 2026 | 1 | 2 | CHC Tool Plan (Aug Conf) - Draft |  |  | Branding
Q2 2026 | 1 | 3 | CHC Tool Plan (Aug Conf) - Final |  |  | Branding